## Sheet1
Phase | Task | Subtask | Total Time (Days) | Total Time (Hours)
Transcription | Transcribe Audio | Use Whisper to transcribe audio files | 2 | 16
| Save Transcription | Save transcribed text in JSON or plain text format | 1 | 8
Text Processing | Pre-process Text | Clean and prepare the transcribed text | 1 | 8
| Analyze Text | Use GPT to analyze and identify formatting needs | 2 | 16
| Response Parser | Create response parser for JSON mapping | 2 | 16
| Apply Formatting | Implement formatting rules using GPT | 2 | 16
Document Formatting | Integrate Text Editor | Choose and integrate a text editor library for formatting | 3 | 24
Admin Panel | Develop UI | Create front end using React Angular or Vue.js | 3 | 24
| Backend Integration | Use Node.js Django or Flask for API requests | 3 | 24
| Save and Export | Provide options for saving document in different formats | 2 | 16
Developer Side Queries:
1.Will you be providing us with the Input Audio and what will be its extension
2.What language will the Audio file be in
3.What will be the average length of Audio Files
4.Will you be providing us with some sample documents with all the correct formatting and text
5.Are you okay with using Paid APIs like OpenAI and other proprietary APIs of Google Docs and Microsoft Documents
Total |  |  | 21 | 168